## Status Report
Project Name |  | E-Appointment System |  |  | Project Manager |  | Sangeeta Joshi
Project Summary |  |  |  | Key Phases | Progress | Status |  | Finish
This system shall be used to handle online appointment for current students, staff and prospect students. By using this system we can avoid wasting time and resources. New students will have access only to the front desk and admission department. Current students will have access to the faculty of their registered courses and some of the teams in the university like ISO. |  |  |  | Kick Off Meeting | 100% | Complete |  | 2016-02-05
|  |  |  | Agree on Objective | 100% | Complete |  | 2016-02-22
|  |  |  | Analysis | 70% | On Track |  | 2016-03-30
|  |  |  | Development | 40% | On Track | Possible Delays | 2016-04-10
|  |  |  | Quality Assurance(Test case writing) | 70% | On Track |  | 2016-03-30
|  |  |  | Quality Assurance(Test Execution) | 0% | Future Task |  | 2016-04-15
|  |  |  | User Acceptance | 0% | Future Task |  | 2016-04-20
|  |  |  | Production | 0% | Future Task |  | TBA
|  |  |  | Support | 0% | Future Task |  | TBA
Tasks Completed |  |  | Tasks Delayed |  | Tasks Planned
Workshop on business requirements. Analysis of the key components. DB design and implementation Development of the key components. |  |  | First release to the QA team. |  | First release to the QA team. Testing of the components.
Key Project Risks and Issues
Type | Risks or Issue Description |  |  |  |  | Mitigation
Issue | Some unplanned leaves have been taken by the project team. There could be some impact to the schedule. |  |  |  |  | We are trying to mitigate that and meet the schedule by speeding the development this week.

## Data
Sl NO | Resources | Status | Issue Type
1 | Nilam | On Track | Issue
2 | Shweta Sahu | Possible Delays | Risk
3 | Ekta Khiani | Delayed
4 | Shravani Edem | Complete
5 | Abdul | Future Task
6 | Sangeeta Joshi