## Release Plan
S.No. | Features | Release Date
1 | Login | 2016-03-29
Prospect Student make appointment
2 | Current Student Schedule appointment | 2016-04-04
Staff - Set up appointment
3 | Current Student-My appointment | 2016-04-08
Staff- My Appointment, with Accept and Reject and Mail
Edit Profile- Srudent/Staff
4 | Admin-Add/Update/Delete User | 2016-04-11
Sign Out