## Release Plan
S.No. | Features | Planned Release Date | Actual Release Date
1 | Login | 2016-03-29 | 2016-04-03
Prospect Student make appointment
2 | Current Student Schedule appointment | 2016-04-04 | 2016-04-07
Staff - Set up appointment
3 | Current Student-My appointment | 2016-04-08 | 2016-04-11
Staff- My Appointment, with Accept and Reject and Mail
Edit Profile- Student/Staff
4 | Admin-Add/Update/Delete User | 2016-04-11 | 2016-04-15
Sign Out